## general_report
Issue Type | Key | Summary | Description | Component/s | Priority | Status | Responsible Party/Person | Target Complete Date | Actual Completion Date | Created | Updated | User | User Department | Vendor Contact Point
| FDTAI-22 | Performance measure | Hit rate count on FDTAI pages or statistics about customer access |  | Medium | On hold IT | FDTAI / Andy Hu | TBC
| FDTAI-21 | Production VPN setup | Production VPN setup |  | Medium | Working at IT | BOCOM / Ricky Chan | 2018-03-16
| FDTAI-20 | TSCI Mobile app banner & introduction page (2nd draft) | TSCI Mobile app banner & introduction page (2nd draft) |  | Medium | Pending vendor reply | Erazoom / Elaine | 2018-03-09
| FDTAI-19 | High CPU Issue of kworker service | High CPU Issue of kworker service |  | High | Pending vendor reply | FDTAI / Andy Hu | 2018-03-09
| FDTAI-18 | Required documents for BOCOM IT policy | - Vendor release note / delivery note (State what the changes/functions in the release) - Vendor QAT test result (Prove the release was tested for the specific changes by the vendor at their environment) - Vendor regression test result (Prove the release was tested for all functions of all modules listed in the regression test plan and cases by the vendor at their environment) - System monitoring and health check document |  | Medium | Pending vendor reply | FDTAI / Andy Hu | 2018-03-16
| FDTAI-17 | Production domain name "ai.bocomgroup.com" DNS setup | Network, DNS setup or etc |  | Medium | Working at IT | BOCOM / Kenny Wong | 2018-03-23 | 2018-03-03
| FDTAI-16 | Production network environment setup | Lease line installation, firewall rules setup and etc |  | Medium | On hold IT | FDTAI / Andy Hu & BOCOM / Ricky Chan | 2018-03-23
| FDTAI-15 | FDTAI production environment setup | FDTAI production environment setup |  | Medium | Pending vendor reply | FDTAI / Andy Hu | 2018-03-23
| FDTAI-14 | Production server delivery and setup | Production server delivery and setup |  | Medium | Pending vendor reply | BOCOM / Kenny Wong | 2018-03-02
New Requirement (User / IT) | FDTAI-13 | Batch job to extract and upload the transaction data to FDTAI gateway | Batch job to extract and upload the transaction data to FDTAI gateway |  | Medium | On hold by IT | BOCOM / Ray Hung | 2018-03-16
New Requirement (User / IT) | FDTAI-12 | TSCI mobile app development | TSCI mobile app development |  | Medium | Pending vendor reply | TSCI / Lisa Chen | 2018-03-16
New Requirement (User / IT) | FDTAI-11 | FDTAI testing environment setup | FDTAI development and testing environment setup |  | Medium | Pending vendor reply | FDTAI / Andy Hu | 2018-02-15
| FDTAI-10 | UAT domain name uatai.bocomgroup.com setup | Network, DNS setup or etc |  | Medium | Resolved | BOCOM / Kenny Wong | 2018-02-15 | 2018-03-03
New Requirement (User / IT) | FDTAI-9 | 1 year transaction data for FDTAI development and testing | Prepare 1 year transaction data for FDTAI development and testing |  | Medium | Resolved | BOCOM / Ray Hung | 2018-02-09 | 2018-02-06
New Requirement (User / IT) | FDTAI-8 | License required on displaying delayed market data in FDTAI pages | License required on displaying delayed market data in FDTAI pages |  | High | Resolved | FDTAI / Andy Hu | 2018-02-02 | 2018-02-02 | 2018-02-02 13:58 | 2018-02-02 14:09 | Ray Hung | Information Technology | FDTAI Andy
New Requirement (User / IT) | FDTAI-7 | FDTAI functions user guide/manual | FDTAI functions user guide/manual |  | Medium | On hold by IT | FDTAI / Andy Hu | 2018-03-16 |  | 2018-02-02 13:53 | 2018-02-02 13:53 | Ray Hung | Information Technology | FDTAI Andy
New Requirement (User / IT) | FDTAI-6 | Arrange SSL certification for FDTAI pages | SSL certification for FDTAI pages |  | Medium | Resolved | BOCOM / Kenny Wong | 2018-02-09 | 2018-08-02 | 2018-02-02 13:49 | 2018-02-02 14:09 | Ray Hung | Information Technology | FDTAI Andy
New Requirement (User / IT) | FDTAI-5 | TSCI Mobile app FDTAI icon (1st draft) | TSCI Mobile app FDTAI icon (1st draft) |  | Medium | Resolved | TSCI / Lisa Chen | 2018-02-09 | 2018-02-09 | 2018-02-02 13:46 | 2018-02-02 13:55 | Ray Hung | Information Technology | TSCI Lisa, FDTAI Andy | EBD Rachel confirmed to use icon designed by FDTAI
New Requirement (User / IT) | FDTAI-4 | TSCI Mobile app banner & introduction page (1st draft) | TSCI Mobile app banner & introduction page (1st draft) |  | Medium | Resolved | Erazoom / Elaine | 2018-02-09 | 2018-02-09 | 2018-02-02 13:44 | 2018-02-02 13:55 | Ray Hung | Information Technology | Erazoom Elaine
New Requirement (User / IT) | FDTAI-3 | UAT VPN setup | VPN connection setup between BOCOM UAT and FDTAI UAT environment |  | Medium | Resolved | BOCOM / Ray Chiang | 2018-02-09 | 2018-02-09 | 2018-02-02 13:23 | 2018-02-02 14:09 | Ray Hung | Information Technology | FDTAI Andy
New Requirement (User / IT) | FDTAI-2 | Citirx logins for FDTAI team to remote access | Citirx logins for FDTAI team to remote access |  | Medium | Resolved | BOCOM / Ray Chiang | 2018-02-08 | 2018-02-12 | 2018-02-02 13:20 | 2018-02-02 14:09 | Ray Hung | Information Technology | FDTAI Andy
New Requirement (User / IT) | FDTAI-1 | Lease line ordering | Two 10M lease lines can support failvover |  | High | Resolved | FDTAI / Andy Hu & BOCOM / Ricky Chan | 2018-02-09 | 2018-02-22 | 2018-02-02 13:16 | 2018-02-02 13:57 | Ray Hung | Information Technology | FDTAI Andy